## Action Plan
Task ID | Task Description | Owner | Start Date | End Date | Duration (HH:MM) | Downtime Required | Status | Responsibility | Dependencies | Notes
1 | Inventory current Linux systems | Infra Team | [7 empty] | Collect OS, hardware, IP details
2 | Validate hardware and software compatibility | Infra Team
3 | OS license & Support check | Compliance | [6 empty] | Task 1 | RHEL/SUSE subscriptions, etc.
4 | Audit & risk assessment | Audit Team |  |  |  |  | Pending |  | Task 1 | Security, patch, and vulnerability scan
5 | Storage usage and capacity assessment | Storage Team |  |  |  |  | Pending |  | Task 1 | LVM usage, SAN/NAS check
6 | Full server backup (or) Backup all critical systems) | Backup Team |  |  |  |  | Pending |  | Task 1 | Snapshot and DB backup
7 | Monitor systems & performance | Ops Team |  |  |  |  | Pending |  | Task 5 | Set up alerts and health checks
8 | Draft rollback and recovery plan | IT Manager |  |  |  |  | Pending |  |  | Include ISO & snapshot-based recovery
9 | Set up test environment | Infra Team |  |  |  |  | Pending |  |  | Clone production config
10 | Perform dry-run upgrade | SysAdmin |  |  |  |  | Pending |  |  | Test upgrade steps
11 | Review dry-run results & finalize SOP | Infra Lead |  |  |  |  | Pending |  |  | Refine documentation
12 | Schedule production upgrade | PMO |  |  |  |  | Pending |  |  | Notify stakeholders
13 | Execute production upgrade | SysAdmin |  |  |  |  | Pending |  |  | Monitor logs and process
14 | Post-upgrade validation and monitoring | QA Team |  |  |  |  | Pending |  |  | Health checks and regression tests
15 | Project closure & documentation | PMO |  |  |  |  | Pending |  |  | Update CMDB and audit trail

## License & Audit
OS Type | Server Count | License Type | Valid Until | Needs Renewal? | Owner | Notes
SUSE 12 SP5 | ?? | SLES | ?? | ?? | Compliance | Renewal auto-scheduled

## Storage Details
Server Name | Mount Point | Allocated Size | Used % | Storage Type | Upgrade Ready?
| / | 100 GB | 68% | SAN | Yes
|  |  |  | NAS | Needs extension
|  |  |  | Local | Archive needed